## Product
PRODUCT BACKLOG
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
0 | Display menu screen on program start | Menu | M | X
1 | Menu with "start game" and "exit" buttons | Menu | M | X
2 | Show the rules of the game when needed by user | Menu or Turn | M | X
3 | Screen to select the number of players | Init | M |  | X
4 | Display game board | Init | M |  | X
5 | Place all pawns on their tile | Init | M | X
6 | Display "exit" button | Init and Turn | M |  | X
7 | Display which player is playing the current turn | Turn | M
9 | Execute special actions (for example, go back to tile 1) according to the tile on which the player arrive | Turn | M
10 | Change current player after the end of the turn | Turn | M |  | X
11 | Show win screen if current player arrives to end tile and display name of winner | End | M |  | X
12 | Make game cards | Init and Turn | M |  | X
13 | Make a base deck | Init and Turn | M |  | X
14 | Add stats to Pawns | Init and Turn | M |  | X
15 | Put Cards on board and add types | Init and Turn | M
16 | Make Special deck | Init and Turn | M |  | X
17 | Make player deck | Init and Turn | M |  | X
18 | Make a Discard deck | Init and Turn | M |  | X
19 | Go back to menu button is displayed in the win screen | End | S
20 | Current player can pause and resume the game | Turn | S
21 | Produce sound for moving pawn / win screen / special actions | Turn | C
22 | Display features/ moving pawn with an animation | Turn | C
23 | Menu extended with "settings" button (for example, containing screen resolution, audio volume, …) | Menu | C
24 | Possibility to select also computer players | Init | C
25 | Computer player is able to play the game | Turn | C
26 | Add some humour to the computer player | Turn | W
27 | Save current state of the game on a file | Turn | C
28 | Load a previously saved game state | Menu | C
29 | Make game playable by users sitting at different PCs (LAN multiplayer) | Menu and Turn | C

## Sprint1
SPRINT BACKLOG 1
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
0 | As a player I want to have a menu with 4 options, so that I can control the game | M | 5:00 | 1. Loading the display with the menu items 2. Showing the text in the middle of the screen 3. Be sure the game screen keeps open when no action performed 4. Create the menu | Having a working menu with 4 options
1 | As a player I want to be able to start and stop the game so that I can play the game and end whenever I want | M | 2:00 | 1. Make start button 2. Make stop button 3. Close the game when pressed on X | Having a start and exit buttons
2 | As a player I want to view the highscore, so that I can view who has the highest score | M | 2:00 | 1. Make a highscore button 2. Go to highscore page | Have a highscore button
6 | As a player I want to read the rules from the game, so that I know how the game works | M | 1:30 | 1. Make rules button 2. Make a rules page | Have a rules button

## Sprint2
SPRINT BACKLOG 2
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
3 | As a player I want to be able to select the amount of players that will participate so that I can play with friends . | M | 1:05 | 1.make buttons to select the amount of players | You can choose the amount of players
4 | As a player I want to see the game board so that I can play the game | M | 1:30 | 1. Design board game. 2. Implement it in game. 3. If you press start and after you choose the amount of players show the board. 4. Make it clickable | The game must have a board and the board must be clear
6 | As a player I want to see the exit button so that I can exit the game easily | M | 0:50 | 1. Create an exit button 2. Make it clickable 3. If you click exit or the X button in the corner it will close | Exit button should be easy to find and working
10 | As a player I want the game to change turns so that each player gets a turn | M | 1:00 | 1. Give players turns 2. Give them options in the turns 3. Make it possible to end a turn 4. Make a time limit per term | The game must give each player a turn and goes on till the end
11 | As a player I want the game to announce the winner so that everyone knows who won at the end | M | 1:30 | 1. Make a win screen 2. Redirect to the win screen after game has ended 3. Save the highscore | At the end of the game , the game must announce the winner
12 | As a player I want the game to have game cards so that we can play with it | M | 1:50 | 1. Make a win screen 2. Redirect to the win screen after game has ended 3. Save the highscore | The game must contain game cards
13 | As a player I want a base deck so that I can start the game easily | M | 2:00 | 1. Make a base deck 2. Make it clickable 3. Make it contain cards 4. If empty replace it with discarded deck | Each player must have a base deck
14 | As a Player I want the Pawns to have stats so that I can tell which pawns beats which | M | 2:10 | 1. Make the different kinds of pawns 2. Give them stats 3. Make given amount of pawns per type 4. Make them different color for each team | Each pawn must have stats
16 | As a player I want a special deck so that I can receive spiecal cards | M | 2:20 | 1. Make a special deck 2. Add special cards 3. Make player be able to receive from this deck | Each player must have a spiecal deck that gives you spiecal cards
17 | As a player I want to have a player deck so that I tell which cards I have | M | 2:40 | 1. Make player decks 2. Add card pulled from the base decks by the player 3. Make them selectable 4. Organize by type | Each player must have a player deck that reviews cards
18 | As a player I want to have a discarded deck so that when I pull a 7th card I can discard it and when the base deck is empty it has a replacement | M | 3:00 | 1. Make a discarded deck 2. Add every 6th card from a player deck into this deck 3. When the base deck contains no cards replace it by this deck | Each player must have a discard deck that is replaceable