## Product
PRODUCT BACKLOG
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
0 | Display menu screen on program start | Menu | M | X
1 | Menu with "start game" and "exit" buttons | Menu | M | X
2 | Show the rules of the game when needed by user | Menu or Turn | M | X
3 | Screen to select the number of players | Init | M |  | X
4 | Display game board | Init | M |  | X
5 | Place all pawns on their tile | Init | M | X
6 | Display "exit" button | Init and Turn | M |  | X
7 | Display which player is playing the current turn | Turn | M
9 | Execute special actions (for example, go back to tile 1) according to the tile on which the player arrive | Turn | M
10 | Change current player after the end of the turn | Turn | M |  | X
11 | Show win screen if current player arrives to end tile and display name of winner | End | M |  | X
12 | Make game cards | Init and Turn | M |  | X
13 | Make a base deck | Init and Turn | M |  | X
14 | Add stats to Pawns | Init and Turn | M |  | X
15 | Put Cards on board and add types | Init and Turn | M
16 | Make Special deck | Init and Turn | M |  | X
17 | Make player deck | Init and Turn | M |  | X
18 | Make a Discard deck | Init and Turn | M |  | X
19 | Go back to menu button is displayed in the win screen | End | S
20 | Current player can pause and resume the game | Turn | S
21 | Produce sound for moving pawn / win screen / special actions | Turn | C
22 | Display features/ moving pawn with an animation | Turn | C
23 | Menu extended with "settings" button (for example, containing screen resolution, audio volume, …) | Menu | C
24 | Possibility to select also computer players | Init | C
25 | Computer player is able to play the game | Turn | C
26 | Add some humour to the computer player | Turn | W
27 | Save current state of the game on a file | Turn | C
28 | Load a previously saved game state | Menu | C
29 | Make game playable by users sitting at different PCs (LAN multiplayer) | Menu and Turn | C

## Sprint1
SPRINT BACKLOG 1
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
0 | As a player I want to have a menu with 4 options, so that I can control the game | M | 5:00 | 1. Loading the display with the menu items 2. Showing the text in the middle of the screen 3. Be sure the game screen keeps open when no action performed 4. Create the menu | Have a working menu
1 | As a player I want to be able to start and stop the game so that I can play the game and end whenever I want | M | 2:00 | 1. Make start button 2. Make stop button 3. Close the game when pressed on X | Have working start and exit buttons
2 | As a player I want to view the highscore, so that I can view who has the highest score | M | 2:00 | 1. Make a highscore button 2. Go to highscore page | Have a highscore button
6 | As a player I want to read the rules from the game, so that I know how the game works | M | 1:30 | 1. Make rules button 2. Make a rules page | Have a rules button

## Sprint2
SPRINT BACKLOG 2
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria | Sprint 3
3 | As a player I want to be able to select the amount of players that will participate so that I can play with friends . | M | 1:05
4 | As a player I want to see the game board so that I can see whats happening | M | 1:30
6 | As a player I want to see the exit button so that I can exit the game easily | M | 0:50
10 | As a player I want the game to change turns to another player so that each player gets a his turn | M
11 | As a player I want the game to announce the winner so that everyone knows who won | M
12 | As a player I want the game to have game cards so that we can play it | M
13 | As a player I want a base deck so that I can start the game easily | M
14 | As a Player I want the Pawns to have stats so that I can tell which pawn beats which | M
16 | As a Player I want a special deck so I can receive spiecal cards | M
17 | As a player I want to have a player deck so that I tell which cards I have | M
18 | As a player I want to have a discarded deck so that when I pull a 7th card I can discard it and when the base deck is empty it has a replacement | M