## Blad1
Projectnaam | User story # | Work item # | Monday - remaining hours | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Day 7
Sprint 2 | User story 4 | Work item 4.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | Make sure you fill in "hours remaining"
Sprint 2 | User story 5 | Work item 5.1 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 2
Sprint 2 | User story 5 | Work item 5.2 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 3
Sprint 2 | User story 5 | Work item 5.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1
Sprint 2 | User story 5 | Work item 5.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 2
Sprint 2 | User story 7 | Work item 7.1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 1
Sprint 2 | User story 7 | Work item 7.2 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 2
Sprint 2 | User story 7 | Work item 7.3 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 1
Sprint 2 | User story 13 | Work item 13.1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 2
Sprint 2 | User story 13 | Work item 13.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Sprint 2 | User story 13 | Work item 13.3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Sprint 2 | User story 14 | Work item 14.1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Sprint 2 | User story 14 | Work item 14.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Sprint 2 | User story 14 | Work item 14.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Sprint 2 | User story 14 | Work item 14.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Sprint 2 | User story 15 | Work item 15.1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Sprint 2 | User story 15 | Work item 15.2 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Sprint 2 | User story 15 | Work item 15.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
Sprint 2 | User story 15 | Work item 15.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Sprint 2 | User story 17 | Work item 17.1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Sprint 2 | User story 17 | Work item 17.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Sprint 2 | User story 17 | Work item 17.3 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Sprint 2 | User story 18 | Work item 18.1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Sprint 2 | User story 18 | Work item 18.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Sprint 2 | User story 18 | Work item 18.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Sprint 2 | User story 18 | Work item 18.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Sprint 2 | User story 19 | Work item 19.1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Sprint 2 | User story 19 | Work item 19.2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Sprint 2 | User story 19 | Work item 19.3 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Ideal | 18 | 16 | 13 | 10 | 7 | 4 | 0 | #REF!
|  | Actual | 18 | 18 | 16.5 | 13.5 | 12 | 10 | 9.5 | 17